## 0. START HERE
QI INTELLIGENCE PLATFORM v9 - choose-only, fully integrated
Graphical - AI-assisted - every sheet linked. You only ever pick from dropdowns.
HOW IT WORKS
| 1 | Open '1. MASTER_ENTRY' and fill ONE row by clicking the dropdown arrows (yellow cells only).
| 2 | RPN, timing, health and an AI recommendation calculate instantly.
| 3 | That single case auto-creates a PM task, scored risk, FMEA line, PDCA cycle, action-log entry and Gantt bar.
| 4 | Open 'DASHBOARD' for live KPIs & charts (change the chart with the D13 dropdown).
| 5 | Open 'AI_ASSISTANT' for a ranked action queue and a Lean playbook advisor.
ALL sheets are locked so you can only choose - never mistype. (Review > Unprotect Sheet to edit structure.)
NAVIGATION
> 1. MASTER_ENTRY
> 2. PM_TASKS
> 3. RISK_REGISTER
> 4. FMEA
> 5. PDCA
> 6. ACTION_LOG
> 7. TIMELINE
> 8. SIX_SIGMA
> DASHBOARD
> AI_ASSISTANT

## 1. MASTER_ENTRY
CHOOSE-ONLY MASTER ENTRY - click dropdowns in the YELLOW columns
Nothing here can be typed. Pick from the lists. GREEN columns auto-calc. Each row drives PM Tasks, Risk, FMEA, PDCA, Action Log, Timeline, Dashboard & AI.
CASE ID (auto) | DATE LOGGED | PROBLEM / CHALLENGE STATEMENT | CATEGORY | PRIORITY | SEV 1-10 | OCC 1-10 | DET 1-10 | RPN (auto) | RPN BAND (auto) | ROOT CAUSE HYPOTHESIS | LEAN METHOD | OWNER | TARGET OUTCOME (MEASURABLE) | START DATE | EST. DAYS (auto) | EST. END (auto) | STATUS | % DONE | HEALTH (auto) | AI RECOMMENDED ACTION (auto-generated)
| 2026-05-15 | Delivery targets missed 20% consistently | Delivery / Schedule | 1-CRITICAL | 8 | 7 | 6 |  |  | Handoff delays invisible; no WIP limits | Value Stream Mapping | PM | On-time delivery >95% in 8 weeks | 2026-06-01 |  |  | IN PROGRESS | 20%
| 2026-05-15 | Defect rate at 12% - customers complaining | Quality / Defects | 1-CRITICAL | 8 | 7 | 6 |  |  | No quality check at source | PDCA | PM | Zero defect escapes within 4 weeks | 2026-06-01 |  |  | OPEN | 0%
| 2026-05-15 | Team overwhelmed, parallel tasks >8 each | Process / Flow | 2-HIGH | 7 | 6 | 5 |  |  | No WIP limits; everything is priority 1 | Kanban | PM | Max 3 active tasks per person | 2026-06-01 |  |  | OPEN | 0%
| 2026-05-15 | Approval bottleneck adds 2.3 days per case | Process / Flow | 2-HIGH | 7 | 6 | 5 |  |  | Wrong routing; unclear decision authority | Standard Work | PM | Approval time <4 hours | 2026-06-01 |  |  | OPEN | 0%
| 2026-05-15 | New hire onboarding takes 6 weeks | Process / Flow | 3-MEDIUM | 6 | 5 | 5 |  |  | No documented process; tribal knowledge | Standard Work | PM | Onboard in 2 weeks, consistent quality | 2026-06-01 |  |  | OPEN | 0%
| 2026-05-15 | Leader not visible to frontline team | Process / Flow | 2-HIGH | 7 | 6 | 5 |  |  | No structured Gemba cadence in place | Gemba Walk | PM | Weekly Gemba walk every leader, every week | 2026-06-01 |  |  | IN PROGRESS | 20%

## 2. PM_TASKS
PM TASK TRACKER - auto-built from every registered case
Read-only. Each task mirrors a MASTER case. Edit on MASTER_ENTRY; this updates instantly.
TASK ID | TASK / DELIVERABLE | OWNER | PRIORITY | START | DUE | EST DAYS | % DONE | STATUS | HEALTH

## 3. RISK_REGISTER
RISK REGISTER - every case scored (RPN = Sev x Occ x Det)
Read-only. RPN band drives escalation. Mitigation method & owner come from the case.
RISK ID | RISK / EXPOSURE | CATEGORY | SEV | OCC | DET | RPN | RPN BAND | MITIGATION METHOD | OWNER | STATUS

## 4. FMEA
FMEA - Failure Mode & Effects Analysis (auto from cases)
Read-only. Area=category, Failure=problem, Cause=root cause. RPN & action auto-fill.
CASE ID | PROCESS / AREA | FAILURE MODE (problem) | POTENTIAL CAUSE | SEV | OCC | DET | RPN | BAND | RECOMMENDED ACTION (AI) | OWNER | STATUS

## 5. PDCA
PDCA CYCLES - one Plan-Do-Check-Act loop per case
Read-only. PLAN=problem, DO=root cause+method, CHECK=target, ACT=AI recommendation.
CASE ID | CYCLE | PLAN (problem) | DO (root cause + method) | CHECK (target) | ACT (AI next step) | STATUS

## 6. ACTION_LOG
ACTION LOG - improvement action captured for every case
Read-only audit trail. Owner, outcome, due date, status all flow from MASTER_ENTRY.
CASE ID | DATE | ACTION TAKEN / PLANNED | OWNER | EXPECTED OUTCOME | STATUS | DUE

## 7. TIMELINE
TIMELINE / GANTT - schedule auto-drawn from each case
Read-only. Start/end/duration are AI-estimated on MASTER_ENTRY. Bars redraw automatically.
CASE ID | TASK | OWNER | START | END | % DONE
| Legend: | Scheduled | Completed

## 8. SIX_SIGMA
SIX SIGMA - defect & Sigma-level trend (live chart)
Choose Units, Defects and Opps/Unit from dropdowns. Defect%, DPMO and Sigma auto-calc.
WEEK | UNITS (choose) | DEFECTS (choose) | OPPS/UNIT (choose) | DEFECT % | DPMO | SIGMA | TARGET
Week 1 | 600 | 72 | 5 |  |  |  | 4.5
Week 2 | 580 | 65 | 5 |  |  |  | 4.5
Week 3 | 610 | 58 | 5 |  |  |  | 4.5
Week 4 | 595 | 50 | 5 |  |  |  | 4.5
Week 5 | 620 | 45 | 5 |  |  |  | 4.5
Week 6 | 605 | 38 | 5 |  |  |  | 4.5
Week 7 | 615 |  | 5 |  |  |  | 4.5
Week 8 |  |  | 5 |  |  |  | 4.5

## DASHBOARD
LIVE DASHBOARD - auto-refreshes from MASTER_ENTRY
Read-only except the dropdown in D13 which changes the main chart grouping.
| TOTAL CASES |  | OPEN / ACTIVE |  | CRITICAL (RPN>=200) | AVG RPN | AVG % DONE |  | BLOCKED
| MAIN CHART - group cases by: |  | Priority | <- change me
| Bucket | Cases
[10 empty] | 1-CRITICAL | OPEN | Quality / Defects | PM
[10 empty] | 2-HIGH | IN PROGRESS | Delivery / Schedule | Dev Lead
[10 empty] | 3-MEDIUM | ON HOLD | Process / Flow | QA Lead
[10 empty] | 4-LOW | BLOCKED | People / Training | Ops Lead
[11 empty] | RESOLVED | Cost / Waste | Architect
[11 empty] | CLOSED | Safety / Compliance | BA
[12 empty] | Technology / Tools | Team Lead
[12 empty] | Customer / VOC | Process Owner
| Status breakdown | [6 empty] | Total RPN by category
| OPEN | [6 empty] | Quality / Defects
| IN PROGRESS | [6 empty] | Delivery / Schedule
| ON HOLD | [6 empty] | Process / Flow
| BLOCKED | [6 empty] | People / Training
| RESOLVED | [6 empty] | Cost / Waste
| CLOSED | [6 empty] | Safety / Compliance
Technology / Tools
Customer / VOC

## AI_ASSISTANT
AI ASSISTANT - live insights & recommended actions
Read-only except the advisor dropdown. Action queue ranked by RPN.
EXECUTIVE SUMMARY (auto-generated)
PRIORITY ACTION QUEUE - ranked by RPN (highest risk first)
| # | CASE ID | PROBLEM | RPN | OWNER | AI RECOMMENDED ACTION
1
2
3
4
5
6
7
8
9
10
11
12
| ASK THE ADVISOR - pick a focus area: |  |  | Quality / Defects

## LISTS (hidden)
Category | Priority | Score | LeanMethod | Owner | Status | Problems | RootCauses | Targets | Percent | Units | Defects | Opps | Dates
Quality / Defects | 1-CRITICAL | 1 | Value Stream Mapping | PM | OPEN | Delivery targets missed 20% consistently | Handoff delays invisible; no WIP limits | On-time delivery >95% in 8 weeks | 0 | 0 | 0 | 1 | 2026-01-01
Delivery / Schedule | 2-HIGH | 2 | Kanban | Dev Lead | IN PROGRESS | Defect rate at 12% - customers complaining | No quality check at source | Zero defect escapes within 4 weeks | 0.1 | 10 | 1 | 2 | 2026-01-02
Process / Flow | 3-MEDIUM | 3 | PDCA | QA Lead | ON HOLD | Team overwhelmed, parallel tasks >8 each | No WIP limits; everything is priority 1 | Max 3 active tasks per person | 0.2 | 20 | 2 | 3 | 2026-01-03
People / Training | 4-LOW | 4 | Standard Work | Ops Lead | BLOCKED | Approval bottleneck adds 2.3 days per case | Wrong routing; unclear decision authority | Approval time <4 hours | 0.3 | 30 | 3 | 4 | 2026-01-04
Cost / Waste |  | 5 | Gemba Walk | Architect | RESOLVED | New hire onboarding takes 6 weeks | No documented process; tribal knowledge | Onboard in 2 weeks, consistent quality | 0.4 | 40 | 4 | 5 | 2026-01-05
Safety / Compliance |  | 6 | Mistake-Proofing / Poka-Yoke | BA | CLOSED | Leader not visible to frontline team | No structured Gemba cadence in place | Weekly Gemba walk every leader, every week | 0.5 | 50 | 5 | 6 | 2026-01-06
Technology / Tools |  | 7 | 5S | Team Lead |  | Instrument calibration behind schedule | No pre-commissioning checklist used | Reduce cycle time by 30% in 8 weeks | 0.6 | 60 | 6 | 7 | 2026-01-07
Customer / VOC |  | 8 | A3 | Process Owner |  | Electrical loop tests failing repeatedly | Inadequate technical review conducted | Cut defect rate below 2% in 6 weeks | 0.7 | 70 | 7 | 8 | 2026-01-08
|  | 9 | Six Sigma DMAIC | DevOps |  | Mechanical punch list not cleared before commissioning | Incomplete P&ID revision control | Reduce WIP to agreed limit within 4 weeks | 0.8 | 80 | 8 | 9 | 2026-01-09
|  | 10 | Root Cause / 5 Whys | Tech Lead |  | Control system commissioning delayed | Poor cable management practices | Improve on-time delivery to >95% | 0.9 | 90 | 9 | 10 | 2026-01-10
|  |  | Kaizen Event | HR |  | FAT defects not resolved before site mobilisation | Insufficient commissioning training | Reduce cost of poor quality by 25% | 1 | 100 | 10 | 11 | 2026-01-11
|  |  | Visual Management | Engineering Lead |  | HAZOP action items not closed | Lack of loop check protocol | Close all critical risks within 2 weeks |  | 110 | 11 | 12 | 2026-01-12
|  |  |  | Commissioning Engineer |  | As-built documentation incomplete or missing | Instrument specification mismatch | Achieve Sigma level >= 4.0 |  | 120 | 12 | 13 | 2026-01-13
|  |  |  | Quality Manager |  | SIL / functional safety testing not completed | No HAZOP / risk review conducted | Zero safety incidents this quarter |  | 130 | 13 | 14 | 2026-01-14
[6 empty] | Long lead equipment delivery delayed | Vendor documentation incomplete or missing | Cut approval lead time to < 4 hours |  | 140 | 14 | 15 | 2026-01-15
[6 empty] | Insufficient qualified commissioning personnel | Construction punch list not cleared | Onboard new hires in <= 2 weeks |  | 150 | 15 | 16 | 2026-01-16
[6 empty] | Permit-to-work bottlenecks causing delays | Software FAT not completed | 100% of cases linked to a countermeasure |  | 160 | 16 | 17 | 2026-01-17
[6 empty] | Inter-discipline coordination failures | Inadequate grounding / earthing design |  |  | 170 | 17 | 18 | 2026-01-18
[6 empty] | Vendor technical support unavailable | Incorrect calibration procedure applied |  |  | 180 | 18 | 19 | 2026-01-19
[6 empty] | Safety case not accepted by regulator | Missing ATEX certification verification |  |  | 190 | 19 | 20 | 2026-01-20
[6 empty] | Software version control issues | No intake checklist |  |  | 200 | 20 |  | 2026-01-21
[6 empty] | Commissioning sequence not agreed | No template / tribal knowledge |  |  | 210 | 21 |  | 2026-01-22
[6 empty] | Electrical isolation procedures missing | No MVP mindset / no WIP limit |  |  | 220 | 22 |  | 2026-01-23
[6 empty] | Mechanical completion not certified | Developer working off informal notes |  |  | 230 | 23 |  | 2026-01-24
[6 empty] | Instrument loop folders incomplete | Test plan not linked to acceptance criteria |  |  | 240 | 24 |  | 2026-01-25
[6 empty] | Control narrative not updated | Manual deploy checklist only |  |  | 250 | 25 |  | 2026-01-26
[6 empty] | Delivery targets missed consistently | No runbook requirement defined |  |  | 260 | 26 |  | 2026-01-27
[6 empty] | Defect rate exceeding acceptable threshold | No communications plan template |  |  | 270 | 27 |  | 2026-01-28
[6 empty] | Team overwhelmed; parallel tasks too high | Routing rule not documented |  |  | 280 | 28 |  | 2026-01-29
[6 empty] | Approval bottleneck causing schedule delay | No mandatory retrospective process |  |  | 290 | 29 |  | 2026-01-30
[6 empty] | New hire onboarding too slow | No commissioning sequence plan issued |  |  | 300 | 30 |  | 2026-01-31
[6 empty] | Change management not followed | HART / fieldbus device not configured |  |  | 310 | 31 |  | 2026-02-01
[6 empty] | Inter-team dependency not managed | As-built drawings not updated |  |  | 320 | 32 |  | 2026-02-02
[6 empty] | Cycle time too long vs customer demand | Process not standardised |  |  | 330 | 33 |  | 2026-02-03
[6 empty] | High work-in-progress / bottleneck forming | No clear ownership / RACI |  |  | 340 | 34 |  | 2026-02-04
[6 empty] | Rework loop consuming team capacity | Insufficient training or skills |  |  | 350 | 35 |  | 2026-02-05
[6 empty] | Customer complaints trending up | Tooling / system limitation |  |  | 360 | 36 |  | 2026-02-06
[6 empty] | Cost overrun against budget | Unclear or changing requirements |  |  | 370 | 37 |  | 2026-02-07
[6 empty] | Safety near-miss reported | Lack of data to make decisions |  |  | 380 | 38 |  | 2026-02-08
[6 empty] | Audit / compliance finding raised |  |  |  | 390 | 39 |  | 2026-02-09
[6 empty] | Knowledge lost when staff leave |  |  |  | 400 | 40 |  | 2026-02-10
[6 empty] | Manual process prone to error |  |  |  | 410 | 41 |  | 2026-02-11
[6 empty] | Handoffs between teams causing delay |  |  |  | 420 | 42 |  | 2026-02-12
[10 empty] | 430 | 43 |  | 2026-02-13
[10 empty] | 440 | 44 |  | 2026-02-14
[10 empty] | 450 | 45 |  | 2026-02-15
[10 empty] | 460 | 46 |  | 2026-02-16
[10 empty] | 470 | 47 |  | 2026-02-17
[10 empty] | 480 | 48 |  | 2026-02-18
[10 empty] | 490 | 49 |  | 2026-02-19
[10 empty] | 500 | 50 |  | 2026-02-20
[10 empty] | 510 | 51 |  | 2026-02-21
[10 empty] | 520 | 52 |  | 2026-02-22
[10 empty] | 530 | 53 |  | 2026-02-23
[10 empty] | 540 | 54 |  | 2026-02-24
[10 empty] | 550 | 55 |  | 2026-02-25
[10 empty] | 560 | 56 |  | 2026-02-26
[10 empty] | 570 | 57 |  | 2026-02-27
[10 empty] | 580 | 58 |  | 2026-02-28
[10 empty] | 590 | 59 |  | 2026-03-01
[10 empty] | 600 | 60 |  | 2026-03-02
[10 empty] | 610 | 61 |  | 2026-03-03
[10 empty] | 620 | 62 |  | 2026-03-04
[10 empty] | 630 | 63 |  | 2026-03-05
[10 empty] | 640 | 64 |  | 2026-03-06
[10 empty] | 650 | 65 |  | 2026-03-07
[10 empty] | 660 | 66 |  | 2026-03-08
[10 empty] | 670 | 67 |  | 2026-03-09
[10 empty] | 680 | 68 |  | 2026-03-10
[10 empty] | 690 | 69 |  | 2026-03-11
[10 empty] | 700 | 70 |  | 2026-03-12
[10 empty] | 710 | 71 |  | 2026-03-13
[10 empty] | 720 | 72 |  | 2026-03-14
[10 empty] | 730 | 73 |  | 2026-03-15
[10 empty] | 740 | 74 |  | 2026-03-16
[10 empty] | 750 | 75 |  | 2026-03-17
[10 empty] | 760 | 76 |  | 2026-03-18
[10 empty] | 770 | 77 |  | 2026-03-19
[10 empty] | 780 | 78 |  | 2026-03-20
[10 empty] | 790 | 79 |  | 2026-03-21
[10 empty] | 800 | 80 |  | 2026-03-22
[10 empty] | 810 | 81 |  | 2026-03-23
[10 empty] | 820 | 82 |  | 2026-03-24
[10 empty] | 830 | 83 |  | 2026-03-25
[10 empty] | 840 | 84 |  | 2026-03-26
[10 empty] | 850 | 85 |  | 2026-03-27
[10 empty] | 860 | 86 |  | 2026-03-28
[10 empty] | 870 | 87 |  | 2026-03-29
[10 empty] | 880 | 88 |  | 2026-03-30
[10 empty] | 890 | 89 |  | 2026-03-31
[10 empty] | 900 | 90 |  | 2026-04-01
[10 empty] | 910 | 91 |  | 2026-04-02
[10 empty] | 920 | 92 |  | 2026-04-03
[10 empty] | 930 | 93 |  | 2026-04-04
[10 empty] | 940 | 94 |  | 2026-04-05
[10 empty] | 950 | 95 |  | 2026-04-06
[10 empty] | 960 | 96 |  | 2026-04-07
[10 empty] | 970 | 97 |  | 2026-04-08
[10 empty] | 980 | 98 |  | 2026-04-09
[10 empty] | 990 | 99 |  | 2026-04-10
[10 empty] | 1000 | 100 |  | 2026-04-11
[10 empty] | 1010 | 101 |  | 2026-04-12
[10 empty] | 1020 | 102 |  | 2026-04-13
[10 empty] | 1030 | 103 |  | 2026-04-14
[10 empty] | 1040 | 104 |  | 2026-04-15
[10 empty] | 1050 | 105 |  | 2026-04-16
[10 empty] | 1060 | 106 |  | 2026-04-17
[10 empty] | 1070 | 107 |  | 2026-04-18
[10 empty] | 1080 | 108 |  | 2026-04-19
[10 empty] | 1090 | 109 |  | 2026-04-20
[10 empty] | 1100 | 110 |  | 2026-04-21
[10 empty] | 1110 | 111 |  | 2026-04-22
[10 empty] | 1120 | 112 |  | 2026-04-23
[10 empty] | 1130 | 113 |  | 2026-04-24
[10 empty] | 1140 | 114 |  | 2026-04-25
[10 empty] | 1150 | 115 |  | 2026-04-26
[10 empty] | 1160 | 116 |  | 2026-04-27
[10 empty] | 1170 | 117 |  | 2026-04-28
[10 empty] | 1180 | 118 |  | 2026-04-29
[10 empty] | 1190 | 119 |  | 2026-04-30
[10 empty] | 1200 | 120 |  | 2026-05-01
[10 empty] | 1210 | 121 |  | 2026-05-02
[10 empty] | 1220 | 122 |  | 2026-05-03
[10 empty] | 1230 | 123 |  | 2026-05-04
[10 empty] | 1240 | 124 |  | 2026-05-05
[10 empty] | 1250 | 125 |  | 2026-05-06
[10 empty] | 1260 | 126 |  | 2026-05-07
[10 empty] | 1270 | 127 |  | 2026-05-08
[10 empty] | 1280 | 128 |  | 2026-05-09
[10 empty] | 1290 | 129 |  | 2026-05-10
[10 empty] | 1300 | 130 |  | 2026-05-11
[10 empty] | 1310 | 131 |  | 2026-05-12
[10 empty] | 1320 | 132 |  | 2026-05-13
[10 empty] | 1330 | 133 |  | 2026-05-14
[10 empty] | 1340 | 134 |  | 2026-05-15
[10 empty] | 1350 | 135 |  | 2026-05-16
[10 empty] | 1360 | 136 |  | 2026-05-17
[10 empty] | 1370 | 137 |  | 2026-05-18
[10 empty] | 1380 | 138 |  | 2026-05-19
[10 empty] | 1390 | 139 |  | 2026-05-20
[10 empty] | 1400 | 140 |  | 2026-05-21
[10 empty] | 1410 | 141 |  | 2026-05-22
[10 empty] | 1420 | 142 |  | 2026-05-23
[10 empty] | 1430 | 143 |  | 2026-05-24
[10 empty] | 1440 | 144 |  | 2026-05-25
[10 empty] | 1450 | 145 |  | 2026-05-26
[10 empty] | 1460 | 146 |  | 2026-05-27
[10 empty] | 1470 | 147 |  | 2026-05-28
[10 empty] | 1480 | 148 |  | 2026-05-29
[10 empty] | 1490 | 149 |  | 2026-05-30
[10 empty] | 1500 | 150 |  | 2026-05-31
[10 empty] | 1510 | 151 |  | 2026-06-01
[10 empty] | 1520 | 152 |  | 2026-06-02
[10 empty] | 1530 | 153 |  | 2026-06-03
[10 empty] | 1540 | 154 |  | 2026-06-04
[10 empty] | 1550 | 155 |  | 2026-06-05
[10 empty] | 1560 | 156 |  | 2026-06-06
[10 empty] | 1570 | 157 |  | 2026-06-07
[10 empty] | 1580 | 158 |  | 2026-06-08
[10 empty] | 1590 | 159 |  | 2026-06-09
[10 empty] | 1600 | 160 |  | 2026-06-10
[10 empty] | 1610 | 161 |  | 2026-06-11
[10 empty] | 1620 | 162 |  | 2026-06-12
[10 empty] | 1630 | 163 |  | 2026-06-13
[10 empty] | 1640 | 164 |  | 2026-06-14
[10 empty] | 1650 | 165 |  | 2026-06-15
[10 empty] | 1660 | 166 |  | 2026-06-16
[10 empty] | 1670 | 167 |  | 2026-06-17
[10 empty] | 1680 | 168 |  | 2026-06-18
[10 empty] | 1690 | 169 |  | 2026-06-19
[10 empty] | 1700 | 170 |  | 2026-06-20
[10 empty] | 1710 | 171 |  | 2026-06-21
[10 empty] | 1720 | 172 |  | 2026-06-22
[10 empty] | 1730 | 173 |  | 2026-06-23
[10 empty] | 1740 | 174 |  | 2026-06-24
[10 empty] | 1750 | 175 |  | 2026-06-25
[10 empty] | 1760 | 176 |  | 2026-06-26
[10 empty] | 1770 | 177 |  | 2026-06-27
[10 empty] | 1780 | 178 |  | 2026-06-28
[10 empty] | 1790 | 179 |  | 2026-06-29
[10 empty] | 1800 | 180 |  | 2026-06-30
[10 empty] | 1810 | 181 |  | 2026-07-01
[10 empty] | 1820 | 182 |  | 2026-07-02
[10 empty] | 1830 | 183 |  | 2026-07-03
[10 empty] | 1840 | 184 |  | 2026-07-04
[10 empty] | 1850 | 185 |  | 2026-07-05
[10 empty] | 1860 | 186 |  | 2026-07-06
[10 empty] | 1870 | 187 |  | 2026-07-07
[10 empty] | 1880 | 188 |  | 2026-07-08
[10 empty] | 1890 | 189 |  | 2026-07-09
[10 empty] | 1900 | 190 |  | 2026-07-10
[10 empty] | 1910 | 191 |  | 2026-07-11
[10 empty] | 1920 | 192 |  | 2026-07-12
[10 empty] | 1930 | 193 |  | 2026-07-13
[10 empty] | 1940 | 194 |  | 2026-07-14
[10 empty] | 1950 | 195 |  | 2026-07-15
[10 empty] | 1960 | 196 |  | 2026-07-16
[10 empty] | 1970 | 197 |  | 2026-07-17
[10 empty] | 1980 | 198 |  | 2026-07-18
[10 empty] | 1990 | 199 |  | 2026-07-19
[10 empty] | 2000 | 200 |  | 2026-07-20
[11 empty] | 201 |  | 2026-07-21
[11 empty] | 202 |  | 2026-07-22
[11 empty] | 203 |  | 2026-07-23
[11 empty] | 204 |  | 2026-07-24
[11 empty] | 205 |  | 2026-07-25
[11 empty] | 206 |  | 2026-07-26
[11 empty] | 207 |  | 2026-07-27
[11 empty] | 208 |  | 2026-07-28
[11 empty] | 209 |  | 2026-07-29
[11 empty] | 210 |  | 2026-07-30
[11 empty] | 211 |  | 2026-07-31
[11 empty] | 212 |  | 2026-08-01
[11 empty] | 213 |  | 2026-08-02
[11 empty] | 214 |  | 2026-08-03
[11 empty] | 215 |  | 2026-08-04
[11 empty] | 216 |  | 2026-08-05
[11 empty] | 217 |  | 2026-08-06
[11 empty] | 218 |  | 2026-08-07
[11 empty] | 219 |  | 2026-08-08
[11 empty] | 220 |  | 2026-08-09
[11 empty] | 221 |  | 2026-08-10
[11 empty] | 222 |  | 2026-08-11
[11 empty] | 223 |  | 2026-08-12
[11 empty] | 224 |  | 2026-08-13
[11 empty] | 225 |  | 2026-08-14
[11 empty] | 226 |  | 2026-08-15
[11 empty] | 227 |  | 2026-08-16
[11 empty] | 228 |  | 2026-08-17
[11 empty] | 229 |  | 2026-08-18
[11 empty] | 230 |  | 2026-08-19
[11 empty] | 231 |  | 2026-08-20
[11 empty] | 232 |  | 2026-08-21
[11 empty] | 233 |  | 2026-08-22
[11 empty] | 234 |  | 2026-08-23
[11 empty] | 235 |  | 2026-08-24
[11 empty] | 236 |  | 2026-08-25
[11 empty] | 237 |  | 2026-08-26
[11 empty] | 238 |  | 2026-08-27
[11 empty] | 239 |  | 2026-08-28
[11 empty] | 240 |  | 2026-08-29
[11 empty] | 241 |  | 2026-08-30
[11 empty] | 242 |  | 2026-08-31
[11 empty] | 243 |  | 2026-09-01
[11 empty] | 244 |  | 2026-09-02
[11 empty] | 245 |  | 2026-09-03
[11 empty] | 246 |  | 2026-09-04
[11 empty] | 247 |  | 2026-09-05
[11 empty] | 248 |  | 2026-09-06
[11 empty] | 249 |  | 2026-09-07
[11 empty] | 250 |  | 2026-09-08
[11 empty] | 251 |  | 2026-09-09
[11 empty] | 252 |  | 2026-09-10
[11 empty] | 253 |  | 2026-09-11
[11 empty] | 254 |  | 2026-09-12
[11 empty] | 255 |  | 2026-09-13
[11 empty] | 256 |  | 2026-09-14
[11 empty] | 257 |  | 2026-09-15
[11 empty] | 258 |  | 2026-09-16
[11 empty] | 259 |  | 2026-09-17
[11 empty] | 260 |  | 2026-09-18
[11 empty] | 261 |  | 2026-09-19
[11 empty] | 262 |  | 2026-09-20
[11 empty] | 263 |  | 2026-09-21
[11 empty] | 264 |  | 2026-09-22
[11 empty] | 265 |  | 2026-09-23
[11 empty] | 266 |  | 2026-09-24
[11 empty] | 267 |  | 2026-09-25
[11 empty] | 268 |  | 2026-09-26
[11 empty] | 269 |  | 2026-09-27
[11 empty] | 270 |  | 2026-09-28
[11 empty] | 271 |  | 2026-09-29
[11 empty] | 272 |  | 2026-09-30
[11 empty] | 273 |  | 2026-10-01
[11 empty] | 274 |  | 2026-10-02
[11 empty] | 275 |  | 2026-10-03
[11 empty] | 276 |  | 2026-10-04
[11 empty] | 277 |  | 2026-10-05
[11 empty] | 278 |  | 2026-10-06
[11 empty] | 279 |  | 2026-10-07
[11 empty] | 280 |  | 2026-10-08
[11 empty] | 281 |  | 2026-10-09
[11 empty] | 282 |  | 2026-10-10
[11 empty] | 283 |  | 2026-10-11
[11 empty] | 284 |  | 2026-10-12
[11 empty] | 285 |  | 2026-10-13
[11 empty] | 286 |  | 2026-10-14
[11 empty] | 287 |  | 2026-10-15
[11 empty] | 288 |  | 2026-10-16
[11 empty] | 289 |  | 2026-10-17
[11 empty] | 290 |  | 2026-10-18
[11 empty] | 291 |  | 2026-10-19
[11 empty] | 292 |  | 2026-10-20
[11 empty] | 293 |  | 2026-10-21
[11 empty] | 294 |  | 2026-10-22
[11 empty] | 295 |  | 2026-10-23
[11 empty] | 296 |  | 2026-10-24
[11 empty] | 297 |  | 2026-10-25
[11 empty] | 298 |  | 2026-10-26
[11 empty] | 299 |  | 2026-10-27
[11 empty] | 300 |  | 2026-10-28
2026-10-29
2026-10-30
2026-10-31
2026-11-01
2026-11-02
2026-11-03
2026-11-04
2026-11-05
2026-11-06
2026-11-07
2026-11-08
2026-11-09
2026-11-10
2026-11-11
2026-11-12
2026-11-13
2026-11-14
2026-11-15
2026-11-16
2026-11-17
2026-11-18
2026-11-19
2026-11-20
2026-11-21
2026-11-22
2026-11-23
2026-11-24
2026-11-25
2026-11-26
2026-11-27
2026-11-28
2026-11-29
2026-11-30
2026-12-01
2026-12-02
2026-12-03
2026-12-04
2026-12-05
2026-12-06
2026-12-07
2026-12-08
2026-12-09
2026-12-10
2026-12-11
2026-12-12
2026-12-13
2026-12-14
2026-12-15
2026-12-16
2026-12-17
2026-12-18
2026-12-19
2026-12-20
2026-12-21
2026-12-22
2026-12-23
2026-12-24
2026-12-25
2026-12-26
2026-12-27
2026-12-28
2026-12-29
2026-12-30
2026-12-31
2027-01-01
2027-01-02
2027-01-03
2027-01-04
2027-01-05
2027-01-06
2027-01-07
2027-01-08
2027-01-09
2027-01-10
2027-01-11
2027-01-12
2027-01-13
2027-01-14
2027-01-15
2027-01-16
2027-01-17
2027-01-18
2027-01-19
2027-01-20
2027-01-21
2027-01-22
2027-01-23
2027-01-24
2027-01-25
2027-01-26
2027-01-27
2027-01-28
2027-01-29
2027-01-30
2027-01-31
2027-02-01
2027-02-02
2027-02-03
2027-02-04
2027-02-05
2027-02-06
2027-02-07
2027-02-08
2027-02-09
2027-02-10
2027-02-11
2027-02-12
2027-02-13
2027-02-14
2027-02-15
2027-02-16
2027-02-17
2027-02-18
2027-02-19
2027-02-20
2027-02-21
2027-02-22
2027-02-23
2027-02-24
2027-02-25
2027-02-26
2027-02-27
2027-02-28
2027-03-01
2027-03-02
2027-03-03
2027-03-04
2027-03-05
2027-03-06
2027-03-07
2027-03-08
2027-03-09
2027-03-10
2027-03-11
2027-03-12
2027-03-13
2027-03-14
2027-03-15
2027-03-16
2027-03-17
2027-03-18
2027-03-19
2027-03-20
2027-03-21
2027-03-22
2027-03-23
2027-03-24
2027-03-25
2027-03-26
2027-03-27
2027-03-28
2027-03-29
2027-03-30
2027-03-31
2027-04-01
2027-04-02
2027-04-03
2027-04-04
2027-04-05
2027-04-06
2027-04-07
2027-04-08
2027-04-09
2027-04-10
2027-04-11
2027-04-12
2027-04-13
2027-04-14
2027-04-15
2027-04-16
2027-04-17
2027-04-18
2027-04-19
2027-04-20
2027-04-21
2027-04-22
2027-04-23
2027-04-24
2027-04-25
2027-04-26
2027-04-27
2027-04-28
2027-04-29
2027-04-30
2027-05-01
2027-05-02
2027-05-03
2027-05-04
2027-05-05
2027-05-06
2027-05-07
2027-05-08
2027-05-09
2027-05-10
2027-05-11
2027-05-12
2027-05-13
2027-05-14
2027-05-15
2027-05-16
2027-05-17
2027-05-18
2027-05-19
2027-05-20
2027-05-21
2027-05-22
2027-05-23
2027-05-24
2027-05-25
2027-05-26
2027-05-27
2027-05-28
2027-05-29
2027-05-30
2027-05-31
2027-06-01
2027-06-02
2027-06-03
2027-06-04
2027-06-05
2027-06-06
2027-06-07
2027-06-08
2027-06-09
2027-06-10
2027-06-11
2027-06-12
2027-06-13
2027-06-14
2027-06-15
2027-06-16
2027-06-17
2027-06-18
2027-06-19
2027-06-20
2027-06-21
2027-06-22
2027-06-23
2027-06-24
2027-06-25
2027-06-26
2027-06-27
2027-06-28
2027-06-29
2027-06-30
2027-07-01
2027-07-02
2027-07-03
2027-07-04
2027-07-05
2027-07-06
2027-07-07
2027-07-08
2027-07-09
2027-07-10
2027-07-11
2027-07-12
2027-07-13
2027-07-14
2027-07-15
2027-07-16
2027-07-17
2027-07-18
2027-07-19
2027-07-20
2027-07-21
2027-07-22
2027-07-23
2027-07-24
2027-07-25
2027-07-26
2027-07-27
2027-07-28
2027-07-29
2027-07-30
2027-07-31
2027-08-01
2027-08-02
2027-08-03
2027-08-04
2027-08-05
2027-08-06
2027-08-07
2027-08-08
2027-08-09
2027-08-10
2027-08-11
2027-08-12
2027-08-13
2027-08-14
2027-08-15
2027-08-16
2027-08-17
2027-08-18
2027-08-19
2027-08-20
2027-08-21
2027-08-22
2027-08-23
2027-08-24
2027-08-25
2027-08-26
2027-08-27
2027-08-28
2027-08-29
2027-08-30
2027-08-31
2027-09-01
2027-09-02
2027-09-03
2027-09-04
2027-09-05
2027-09-06
2027-09-07
2027-09-08
2027-09-09
2027-09-10
2027-09-11
2027-09-12
2027-09-13
2027-09-14
2027-09-15
2027-09-16
2027-09-17
2027-09-18
2027-09-19
2027-09-20
2027-09-21
2027-09-22
2027-09-23
2027-09-24
2027-09-25
2027-09-26
2027-09-27
2027-09-28
2027-09-29
2027-09-30
2027-10-01
2027-10-02
2027-10-03
2027-10-04
2027-10-05
2027-10-06
2027-10-07
2027-10-08
2027-10-09
2027-10-10
2027-10-11
2027-10-12
2027-10-13
2027-10-14
2027-10-15
2027-10-16
2027-10-17
2027-10-18
2027-10-19
2027-10-20
2027-10-21
2027-10-22
2027-10-23
2027-10-24
2027-10-25
2027-10-26
2027-10-27
2027-10-28
2027-10-29
2027-10-30
2027-10-31
2027-11-01
2027-11-02
2027-11-03
2027-11-04
2027-11-05
2027-11-06
2027-11-07
2027-11-08
2027-11-09
2027-11-10
2027-11-11
2027-11-12
2027-11-13
2027-11-14
2027-11-15
2027-11-16
2027-11-17
2027-11-18
2027-11-19
2027-11-20
2027-11-21
2027-11-22
2027-11-23
2027-11-24
2027-11-25
2027-11-26
2027-11-27
2027-11-28
2027-11-29
2027-11-30
2027-12-01
2027-12-02
2027-12-03
2027-12-04
2027-12-05
2027-12-06
2027-12-07
2027-12-08
2027-12-09
2027-12-10
2027-12-11
2027-12-12
2027-12-13
2027-12-14
2027-12-15
2027-12-16
2027-12-17
2027-12-18
2027-12-19
2027-12-20
2027-12-21
2027-12-22
2027-12-23
2027-12-24
2027-12-25
2027-12-26
2027-12-27
2027-12-28
2027-12-29
2027-12-30
2027-12-31